## Sheet1
ID | Risk Author | Date Register | Risk Category | Risk Description | Propability X Impact | Proximity | Response Category | Status | Risk Owner | Risk Actionee
1 | R.A.G.U.T.Rajapaksha | 14/07/2022 | Organizational | Group members cannot meet and discuss about the project due to the transport issues in Sri Lanka. | Low | Medium | Active | Low | R.A.G.U.T.Rajapaksha (RM) | Layan Perera (QM)
2 | R.A.G.U.T.Rajapaksha | 14/07/2022 | Technical | Frequent power failures in Sri Lanka impacting the group's performance. | Medium | High | Active | Increasing | R.A.G.U.T.Rajapaksha (RM) | Bhathiya Kannangara (PM)
3 | R.A.G.U.T.Rajapaksha | 14/07/2022 | Technical | Group members live in different locations and have different power cut schedules. | Low | High | Active | Medium | R.A.G.U.T.Rajapaksha (RM) | Ruwanthi Narampanawa (SM)
4 | R.A.G.U.T.Rajapaksha | 14/07/2022 | Organizational | Group members cannot visit the company due to the transport issues in Sri Lanka. | Low | Low | Active | Increasing | R.A.G.U.T.Rajapaksha (RM) | Imanka Jayasiriwardhana (Startup M.)
5 | R.A.G.U.T.Rajapaksha | 21/07/2022 | Medical | Team members not being able to complete their tasks due to illness like Covid-19. | High | Medium | Active | Medium | R.A.G.U.T.Rajapaksha (RM) | R.A.G.U.T.Rajapaksha (RM)
6 | R.A.G.U.T.Rajapaksha | 14/07/2022 | Economical | Depreciation of the rupee. | High | High | Close | Low | R.A.G.U.T.Rajapaksha (RM) | Imanka Jayasiriwardhana (SM)